## Sheet1
LYMEC events check list
Description | LYMEC Bureau | Seminar team | LYMEC Office | Locals | Done
Pre - Prepreparation
Contact the MO and agree on the location, date and responsibilities | x
Agree with the MO on the budget | x
Sign a contract | x
Send a call for participants |  |  | x
Collect participants and send the list to local organisers with the rooming list |  |  | x
Description | LYMEC Bureau | Seminar team | LYMEC Office | Locals | Done
Preparation
Finding a hotel |  |  |  | x
Agreeing with LYMEC on the hotel | x |  | x | x
Booking and paying the hotel |  |  | x | x
Booking the resturants |  |  |  | x
Booking leisure (if needed) |  |  |  | x
Agreeing on the Conference room |  |  | x | x
Booking the conference room |  |  |  | x
Payment of the conference room |  |  | x
Arranging the transportation of the participants if needed |  |  |  | x
Payment of the transportation |  |  | x
Gether the information for the technical information reader and send it to the LYMEC Office |  |  |  | x
Make sure there is internet in the conference room |  |  |  | x
Congress: Appoint two persons s the event assistants who will assist LYMEC Office on the event |  |  |  | x
Arrange printing of documents (seminar: nothing, congress: 5 congress books) |  |  |  | x
Payment of the print |  |  | x
Arrange the speakers | x | x |  | x
Arrange the speakers fees | x | x | x | x
Define the program of the event | x | x |  | x
Make a detailed division of the responsibilities in the program | x | x
Take care of the protocol if needed |  |  |  | x
Make sure to have a laptop in the conference room |  |  |  | x
Make sure there is a projector in the conference room |  |  |  | x
Congress: Have a printer attached to the laptop tested in advance |  |  |  | x
Congress: Have a stack of papers for printing |  |  |  | x
Congress: Volunteer your members as the scruteneers |  |  |  | x
Seminar: Set up one table in front of the conference for registrations |  |  |  | x
Congress: set up two tables for the registrations |  |  |  | x
Bring the promotional materials to the venue |  |  | x
Make an online reader of the event |  |  | x
Make name tags |  |  | x
Send invoices for the fees |  |  | x
Send an arrival times form to the participants |  |  | x
Provide the final arrival times to the local organisers |  |  | x
Draft one page program document |  |  | x
Congress: Agenda | x
Congress: Program of the congress |  |  | x | x
Congress: draft a powerpoint |  |  | x
Buy chocolate |  |  | x
Congress: Skype meeting with the chairs | x
Seminar: Skype meeting Seminar team | x | x | x | x
Provide the Chairs with RoA, Statutes, policy book |  |  | x
Reserve the room for the cultural evening for the fist night |  |  |  | x
Appoint an IT person who will also take photos (minimum of 10 photos) |  |  |  | x
Congress: Ensure the streem of the Congres or the least video recording |  |  |  | x
Create online Facebook event with the confirmed participants |  |  |  | x
Visa issues: LYMEC Office drafts and local organisers send the visa invit. |  | x |  | x
Description | LYMEC Bureau | Seminar team | LYMEC Office | Locals | Done
On the spot
Restaurants: Payment on spot |  |  | x
Leisure: Payments on spot |  |  | x
Print out the urgent documents |  |  | x
Set up the registration tables |  |  | x | x
Have the overview of spending |  |  | x
Travel refunds Belarus |  |  | x
Collect participation fees |  |  | x
Collect the membership fees | x
Description | LYMEC Bureau | Seminar team | LYMEC Office | Locals | Done
After the event
Event report two days after the event |  | x
Travel refunds two weeks after the event |  |  | x
Publish news on the web site, upload photos on Facebook and Web |  |  | x
Provide the photos to LYMEC office |  |  |  | x
Provide the videos to LYMEC Office |  |  | x
Congress: Update Statutes |  |  |  | x
Congress: Update Policy Book |  |  |  | x
Congress: Update RoP |  |  |  | x
Print out the final list of participants |  |  |  | x
Send the late cancellation fees and the fees not paid yet |  |  |  | x
Follow up the decisions on the Congress | x
Draft and send the letter of graditude to the local organisers | x |  | x